## Sheet1
2026
| Project Start Date: | 2026-09-04 | [5 empty] | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Deadline
| Project Name: | Centavo AI |  |  |  |  | Week Starting | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04
# | Activity | Assigned to | Start | End | Days | Status | %Done
1 | Project Kick-off | Everyone | Sept-4-2026 | Sept-4-2026 | 1 | Done | 100% | bar: 2026-09-04
2 | Project Proposal | Everyone | Sept-4-2026 | Sept-7-2026 | 3 | Done | 100% | bar: 2026-09-04
3 | Requirements - Confirm core workflow | Everyone | Sept-9-2026 | Sept-9-2026 | 1 | Done | 100% | bar: 2026-09-04
4 | Account management CRUD | Giancarlo | Sept-22-2026 | TBD | 36 | In Progress | 75% | bar: 2026-09-18 to 2026-10-23
5 | AI - Connect to Gemini API | Giancarlo | Sept-18-2026 | Oct-8-2026 | 18 | Done | 30% | bar: 2026-09-18 to 2026-10-02
6 | AI - User confirmation screen | Giancarlo | Oct-6-2026 | TBD |  | In Progress | 60% | bar: 2026-10-16 to 2026-10-23
7 | AI - Validate structured output | Giancarlo | Sept-22-2026 | Oct-8-2026 | 14 | Done | 70% | bar: 2026-09-18 to 2026-10-02
8 | Budgets & savings goals | Giancarlo | Sept-25-2026 | TBD | 33 | In Progress | 80% | bar: 2026-09-25 to 2026-10-23
9 | Cloud service selection & setup | Giancarlo/Jensen | Sept-11-2026 | Sept-11-2026 | 1 | Done | 100% | bar: 2026-09-11
10 | Dashboard & calculations | Giancarlo | Sept-16-2026 | TBD | 42 | In Progress | 60% | bar: 2026-09-11 to 2026-10-23
11 | Interface screens & validation | Giancarlo | Sept-16-2026 | TBD | 42 | In Progress | 50% | bar: 2026-09-11 to 2026-10-23
12 | Project Foundation - React & Express setup | Giancarlo | Sept-15-2026 | TBD | 43 | In Progress | 70% | bar: 2026-09-11 to 2026-10-23
13 | Transaction entry & forms | Giancarlo | Sept-22-2026 | TBD | 36 | In Progress | 50% | bar: 2026-09-18 to 2026-10-23
14 | Project Foundation - Repo & branch structure | Giancarlo/ Jensen | Sept-4-2026 | Sept-23-2026 | 20 | Done | 100% | bar: 2026-09-04 to 2026-09-25
15 | Database schema (initial) | Jensen | Sept-16-2026 | Sept-20-2026 | 5 | Done | 100% | bar: 2026-09-11 to 2026-09-18
16 | Define database entities | Jensen | Oct-2-2026 | Oct-25-2026 | 24 | Done | 100% | bar: 2026-10-09 to 2026-10-23
17 | Deployment documentation | Jensen/Marcos | Spt-4-2026 | TBD | 54 | In Progress | 60% | bar: 2026-09-04 to 2026-10-23
18 | Environment config & setup | Jensen/Marcos | Oct-6-2026 | TBD |  | Not Started | 0 | bar: 2026-10-02 to 2026-10-23
19 | Web Deployment | Jensen/Steeve | TBD | TBD |  | Not Started | 0
20 | Web Design | Steeve | Sept-20-2026 | TBD | 38 | In Progress | 80% | bar: 2026-09-18 to 2026-10-23
21 | Business Consultant | Steeve | TBD | TBD |  | Not Started | 0
22 | Market Research | Stevee | Sept-17-2026 | TBD | 41 | In Progress | 70% | bar: 2026-09-11 to 2026-10-23
23 | Wire Framing and CSS layouts | Jensen/Steeve | Sept-23-2026 | Oct-4-2026 | 12 | Done | 100% | bar: 2026-09-18 to 2026-10-02
24 | End-to-end & responsive testing | Marcos | TBD | TBD |  | Not Started | 0
25 | Final Documentation & Presentation | Marcos | TBD | TBD |  | Not Started | 0
26 | Unit & integration tests | Marcos | TBD | TBD |  | Not Started | 0
27 | Validation & error handling tests | Marcos | TBD | TBD |  | Not Started | 0